Guide 2. APT Project Development

Capstone Course

1. APT Project Progress Summary

Below you will find several fields that you must complete with the requested information.

| APT project progress summary | Overall status. As of 01-10-2026, the SICAF project —Comprehensive Attendance Control System Using Facial Recognition, developed for Colegio Polivalente Los Aromos in the municipality of Maipú— is on schedule with respect to the Gantt Chart (10-08-2026 to 05-12-2026). 342 of the 1,309 planned person-hours have been completed, equivalent to 26.1% of the total effort, with no accumulated deviation.. Completed activities. In the planning phase, the Project Charter was drafted and approved, the general requirements were defined, and the team was organized through the RACI Responsibility Matrix. In the analysis and design phase, 42 requirements (R.1 to R.42) were consolidated in the Requirements Spreadsheet, and the extended use cases, the 13 interface mockups, the Software Requirements Specification (SRS) and the Software Architecture Document (SAD) based on the 4+1 views were produced. In the development phase, the Docker container environment was implemented, the PostgreSQL database was built with 32 normalized tables distributed across nine modules, and the system's four microservices were set up: Academic Management, Attendance, Facial Recognition and Reports. Specific objectives achieved. The specific objective of centralizing academic management has been achieved: the operations for students, courses, teachers, subjects, schedules and academic periods are operational in the Academic Management microservice. The objective of ensuring security and role-based access control has also been achieved, through authentication with JWT tokens that expire after eight hours, passwords hashed with bcrypt, headers secured with Helmet.js, and a CORS policy restricted to authorized origins. The objective of generating attendance and academic reports is implemented in the Reports microservice, pending formal validation. The objective of automating attendance recording through facial recognition is implemented and undergoing threshold and performance tuning. Progress against the plan. Module construction was brought forward relative to the Gantt Chart: the four microservices were scheduled to 5 and 7 (October and early November) and are already implemented. This slack will be devoted to the quality assurance, manuals and closure activities, which carry the highest risk because they are concentrated at the end of the schedule. Adjustments to objectives and methodology. No adjustments were made to the objectives or the methodology defined in the previous phase. Both are reproduced in the following sections for verification purposes. |
| --- | --- |
| Objectives | No adjustments. The objectives committed to in the Project Charter remain unchanged. They are reproduced below. General objective. Develop and implement a web-based school attendance control system using facial recognition that automates attendance recording and delivers real-time reports. Success indicator: system deployed and operational with its four modules and facial recognition working under normal conditions of use. Specific objective 1. Automate attendance recording through facial recognition. Indicator: correct recognition in 90% or more of cases and a marking time of less than five seconds per student. Specific objective 2. Centralize the academic management of students, courses, schedules and grades. Indicator: 100% of create, read, update and delete operations operational and validated. Specific objective 3. Generate attendance and academic reports. Indicator: class register, grade report and attendance alerts below 85% correctly generated in PDF and CSV format. Specific objective 4. Ensure security and role-based access control. Indicator: JWT authentication and administrator and teacher roles, with passwords encrypted using bcrypt. |
| Methodology | With adjustments. A Waterfall lifecycle methodology will be used: the scope, architecture, and data model are defined in the initial phases, and the system modules are built incrementally, validating each one before starting the next. This methodology is suitable given that the project presents a low level of risk and uncertainty, as it does not require constant changes or adjustments to the requirements. The use of this methodology in a small project with known stages allows for simple, orderly, and predictable management, optimizing resources and ensuring the fulfillment of objectives without introducing unnecessary complexity. The scope, requirements, and architecture are defined in the initial phases, while construction is carried out incrementally, validating each module before starting the next. Project management is supported by PMBOK practices (project charter, work breakdown structure [WBS], RACI responsibility assignment matrix, risk matrix, and change control), and construction is based on known and reliable practices. Phases and procedures. The project is organized into five phases: planning, analysis and design, development, testing and quality assurance, and implementation and closure. These phases are distributed between 10-08-2026 and 05-12-2026. The construction sequence respects the technical dependencies of the solution: database and architecture, followed by the academic module, then attendance, next facial recognition, followed by reports, and finally container deployment. Methodology relevance. This choice is relevant for two reasons. First, the biometric component demands a defined architecture and data model prior to construction, as the handling of sensitive personal data depends on them and they do not allow for late redesign; hence the predictive nature of the initial phases. Second, facial recognition requires experimental tuning—similarity threshold, response times, and performance under variable lighting—which can only be refined through successively tested increments; hence the incremental nature of the construction. Furthermore, timely planning allows alignment of closures with the delivery milestones committed to the client. |
| Progress evidence | Evidence presented. The following products are presented as evidence for this progress report: the project management documentation (Project Charter, WBS Matrix with the budget, Gantt Chart, RACI Matrix, Risk Matrix and Change Control Matrix); the technical documentation (Spreadsheet of 42 requirements, Extended Use Case Document, Software Requirements Specification, Software Architecture Document with the 4+1 views, Business Process Document with the AS-IS and TO-BE BPMN diagrams, and the 13 interface mockups); the system's source code repository, with the four microservices and the frontend; the init.sql database creation script with its 32 tables and the associated migration script; the docker-compose.yml orchestration file that deploys the complete solution. Justification of the evidence. This evidence demonstrates the project's development because it covers the complete traceability chain and allows it to be verified end to end: each of the 42 requirements can be followed to its use case, from there to the data model tables, and finally to the module that implements it. The management documentationdemonstrates control of scope, cost and schedule; the code and scripts demonstrate actual construction and not just design; and report demonstrates periodic monitoring of progress. Safeguarding quality through discipline. Project quality was safeguarded by applying software development standards. The requirements specification follows the structure of the IEEE 830 standard and the architecture document follows Kruchten's 4+1 view model, so both can be reviewed against a recognized reference and not against an ad hoc criterion. The data model is normalized into 32 tables with their keys and referential integrity declared in the script, which prevents inconsistencies by design instead of correcting them in code. Security was implemented with established practices: JWT tokens with a limited expiration, passwords hashed with bcrypt, HTTP headers secured with Helmet.js, a restricted CORS policy, and a database on an internal network with no exposed port. Deployment in Docker containers ensures that the environment is reproducible and that what was tested is identical to what is installed. Finally, since the system handles biometric data of minors, the principle of minimization was applied: the system stores only the 128-dimension numeric descriptor and never the image of the face, in accordance with Laws No. 19,628 and No. 21,719 on personal data protection. |
| 2. Work Plan Monitoring |
| Carefully review your work plan, focusing especially on the progress status and adjustments columns. |

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activities | Resources | Activity duration | Person responsible | Observations | Progress status | Adjustments |
| IT project management | Drafting and approval of the project Charter | Charter template, PMBOK practices, meetings with the client | 10 days (60 h) | Maximiliano Castillo (Project Manager) | Enabler: the scope was limited by the client from the start. Difficulty: adjusting the budget so that it matched the WBS Matrix exactly. | Completed | The Charter total was made equal to the total person-hours in the WBS Matrix ($6,545,000) and the commercial margin was removed. |
| Requirements analysis and specification | Definition of general requirements and capture of specific requirements | Requirements Spreadsheet, interviews with functional users | 10 days (56 h) | Francisco Jara (Analyst Programmer) | Enabler: the school's business process was already known. Difficulty: delimiting the scope of the academic module. | Completed | 42 requirements (R.1 to R.42) were consolidated with their traceability matrix. |
| IT project management | Team organization and role assignment through the RACI Matrix | RACI Matrix, WBS Matrix, Gantt Chart | 5 days (28 h) | Maximiliano Castillo (Project Manager) | Difficulty: a new member joined the team after the project had started. | Adjusted | Dilan Nuñez was brought in as Quality and Testing, and the RACI Matrix, Gantt Chart, WBS Matrix and Project Charter were updated. |
| Software architecture design | Drafting of the Software Architecture Document (SAD) based on the 4+1 view model | SAD template, draw.io, Kruchten's 4+1 model | 5 days (22 h) | Maximiliano Castillo (Project Manager) | Enabler: the microservices architecture had already been decided. Difficulty: completing all the views required by the format. | Completed | A section on other background and considerations was added, covering security decisions, legal framework and operational continuity. |
| Requirements analysis and specification | Drafting of the extended use case document | Extended use case template, UML diagrams | 5 days (16 h) | Francisco Jara (Analyst Programmer) | Enabler: the requirements were already consolidated and numbered. | Completed | No adjustments. |
| User interface design | Construction of the interface prototypes (system mockups) | draw.io, 13 screens per module and navigation menu | 5 days (28 h) | Maximiliano Castillo (Designer) | Enabler: it allowed the layout of information to be validated with the client before building. | Completed | No adjustments. |
| Requirements analysis and specification | Drafting of the proposed Software Requirements Specification (SRS) | SRS template, IEEE 830 standard | 5 days (22 h) | Maximiliano Castillo (Project Manager) | Difficulty: keeping the figures consistent with the rest of the project documents. | Completed | The figures for database tables (32), requirements (42) and person-hours (1,309) were unified across all documents. |
| Infrastructure and deployment | Implementation of the containerized development environment | Docker, Docker Compose, Node.js, PostgreSQL | 5 days (14 h) | Francisco Jara (Analyst Programmer) | Enabler: the whole environment starts with a single command, which reduced the setup time for each team member. | Completed | No adjustments. |
| Database design and implementation | Modeling and implementation of 32 normalized tables (init.sql script) | PostgreSQL, init.sql script, nine functional modules | 4 days (36 h) | Sebastián Hurtado (Database Administrator) | Difficulty: normalizing the academic model without losing the traceability of the attendance record. | Completed | The documented table count was corrected from 30 to 32, along with the grouping into nine modules. |
| Database design and implementation | Creation of the database query and migration scripts | PL/pgSQL, idempotent migration script | 3 days (36 h) | Sebastián Hurtado (Database Administrator) | Enabler: the scripts are idempotent, so they can be reapplied to an existing database without risk of data loss. | Completed | A migration was added for the holidays table, with the 16 legal holidays of 2026 needed for the attendance calculation. |
| Application security and data protection | Implementation of JWT authentication, login and role-based access control | Node.js, JWT, bcrypt, Helmet.js | 2 days (24 h) | Francisco Jara (Analyst Programmer) | Enabler: mature, widely tested libraries were used. Difficulty: defining the token expiration time. | Completed | Token with an eight-hour expiration, in line with the school day, and passwords stored with a bcrypt hash. |
| Web application development | Academic Management Module (API1): students, courses, teachers, subjects, schedules and academic periods | Node.js, Express, PostgreSQL | 10 days (140 h) | Francisco Jara (Analyst Programmer) | Enabler: the module's operations share a repeatable structure, which sped up construction. | Completed | Construction brought forward relative to the Gantt Chart, which scheduled it from 02-10-2026. |
| Application security and data protection | Implementation of the audit middleware (operations log) | Node.js, log table of the data model | 2 days (28 h) | Francisco Jara (Analyst Programmer) | Enabler: it was implemented as cross-cutting middleware, so it covers all routes without modifying them one by one. | Completed | The middleware is applied in the Academic and Attendance microservices, which concentrate the writes to the school's data. |
| Web application development | Attendance Module (API2): manual marking, draft and final states, percentage calculation and holidays | Node.js, PostgreSQL, holidays table | 8 days (128 h) | Francisco Jara (Analyst Programmer) and Sebastián Hurtado (Database Administrator) | Difficulty: the attendance percentage calculation must exclude legal holidays so as not to penalize students for non-school days. | Completed | Manual marking was left as a direct path to the attendance record, bypassing the facial descriptor comparison, correcting the original BPMN flow. |
| Web application development | Facial Recognition Module (API3): face-api.js, 128-dimension descriptor, Euclidean distance and configurable threshold | face-api.js, WebSocket server, webcam or IP camera | 17 days (254 h) | Maximiliano Castillo (Designer) and Dilan Nuñez (Quality and Testing) | Difficulty: defining how the system should respond when it does not recognize a student, and the fact that camera access from the browser requires a secure context (HTTPS or localhost), which constrains deployment. | In progress | If the face is not recognized, the system reports "Face not recognized", logs the attempt and the teacher marks attendance manually. The distance threshold is configurable from the biometric settings. |
| Web application development | Reports Module (API4): class register, grade report and attendance alerts below 85% | Node.js, pdfkit, CSV export | 8 days (128 h) | Francisco Jara (Analyst Programmer) | Difficulty: generating Excel spreadsheets added dependencies that were not justified by the school's data volume. | Adjusted | Reports are delivered in PDF and CSV instead of Excel. The change is recorded and authorized in the Change Control Matrix. |
| Infrastructure and deployment | Dockerfile per microservice, internal container network and Nginx serving the frontend | Docker, Docker Compose, Nginx | 5 days (77 h) | Francisco Jara (Analyst Programmer) | Enabler: the database stays on Docker's internal network without exposing its port externally, so only the microservices can reach it. | Completed | The frontend derives the API addresses from the request host, which allows the system to be accessed from other computers on the local network without reconfiguring it. |
| Quality assurance and testing | Implementation of the test environment and execution of functional tests | Isolated test environment, test cases and integration checklist | 3 days (38 h) | Dilan Nuñez (Quality and Testing) | Difficulty: to date, validations have been manual, with no automated tests to serve as a safety net against changes. | Not started | Scheduled for 8 (16-11 to 29-11). Validation is being brought forward module by module as each one is closed, instead of concentrating it at the end. |
| Quality assurance and testing | User testing and measurement of recognition accuracy under different lighting conditions | Volunteers, camera, quality indicators log | 5 days (70 h) | Dilan Nuñez (Quality and Testing) | Difficulty: the real end users would be minors, so testing will be carried out with adult volunteers from the team and close circle. | Not started | New activity added to the plan to support the accuracy indicator of 90% or higher committed to in the Project Charter. |
| Technical documentation and handover | Migration to production, training sessions, user and installation manuals, and project closure report | School's local server, manuals, closure report template | 5 days (104 h) | Maximiliano Castillo (Project Manager) | Enabler: container-based deployment simplifies installation on the school's server, since it does not require configuring dependencies manually. | Not started | Scheduled for 8 and 9 (November and December), in accordance with the Gantt Chart. |

3. Adjustments Based on Monitoring

Look more closely at the observations in your work plan. Analyze the planned activities and point out which aspects facilitated or hindered the execution of the plan. Explain how you addressed and/or will address the obstacles. Finally, indicate the adjustments you made to the work plan based on this analysis.

Factors that have facilitated and/or hindered the development of my work plan: Facilitating factors. The first was having reusable prior technical documentation, which allowed the effort to be focused on the formal specification instead of starting from scratch. The second was the early definition of roles in the RACI Matrix, which avoided duplicated work and deliverables without an owner. The third was the exclusive use of open-source tools —Node.js, PostgreSQL, Docker, Nginx and face-api.js—, which eliminated waiting for licenses and licensing costs for the school. The fourth was container-based deployment, which makes it possible to start the entire environment with a single command and ensures that each team member's environment is identical. Difficulties and actions taken. The first difficulty was maintaining consistency between documents: when adapting the documentation to the requested format, discrepancies appeared, such as WBS Matrix hour totals that did not match the sum of the activities and differences in the number of database tables from one document to another. The action taken was to replace the hand-written totals with formulas that add up the activities of each phase, so that the total cost is calculated automatically, and to establish a cross-review of key figures before each delivery. The second difficulty was the arrival of a new team member, Dilan Nuñez, after the project had started, which required updating all the documents already issued and redistributing the activities. The action taken was to formalize his Quality and Testing role in the RACI Matrix, the Gantt Chart, the WBS Matrix and the Charter. The third difficulty was technical: defining how the system should respond when facial recognition fails to identify a student. The action taken was to resolve that in that case the system reports "Face not recognized", records the attempt in the technical log of recognition attempts, and the teacher marks attendance manually, a path that goes directly to the record without going through the descriptor comparison; and to leave the attendance alert below 85% as a separate process, handled by the reports module, which notifies the guardian. Both decisions were modeled in the TO-BE BPMN diagram. The fourth difficulty is that camera access from the browser requires a secure context, which constrains how the system can be demonstrated. The planned action is to run the demonstration on the local machine or, if network access is required, to enable a certificate on the Nginx server that already serves the frontend.

Activities adjusted or eliminated: No activities were eliminated. No activity in the work plan was eliminated. The 20 committed activities remain and add up to the project's 1,309 person-hours, so the scope and the direct cost of $6,545,000 remain unchanged. Adjustment 1: report format. The system's reports are delivered in PDF and CSV instead of Excel. The justification is technical: generating Excel spreadsheets added dependencies that were not justified by the school's data volume, whereas the CSV format is open, opens directly in any spreadsheet application and serves the same purpose of data analysis. The change was formally recorded and authorized in the Change Control Matrix, rather than being applied de facto. Adjustment 2: addition of the Quality and Testing role. The team organization activity was reformulated to incorporate Dilan Nuñez in the Quality and Testing role, which required redistributing responsibility for the functional tests and the user tests. The justification is that the project did not have a role dedicated to quality assurance, which is critical in a biometric system whose success indicator is a measured accuracy rate. Adjustment 3: construction brought forward. The construction activities for the four microservices were brought forward relative to the Gantt Chart dates. The justification is risk management: the schedule concentrates testing, manuals and closure in the last three weeks, so bringing construction forward creates slack precisely where the plan is tightest. The dates of the delivery milestones were not modified. Adjustment 4: Distributed quality validation. Testing will no longer be concentrated in 8 and will also be run module by module as each one is closed. The justification is that concentrating all verification at the end accumulates defects in the stretch of the schedule with the least slack to correct them. New activity added. The implementation of the informed consent record for the processing of biometric data was added to the plan, identified while reviewing the data model. The justification is legal: the system processes biometric data of minors, and Laws No. 19,628 and No. 21,719 on personal data protection require the consent of the data subject or their representative for such processing. The activity is assigned to the Database Administrator and the Analyst Programmer.

Activities that you have not started or that are delayed: No activity is delayed. As of 01-10-2026, no activities are behind the Gantt Chart. Effort progress is 342 of 1,309 person-hours (26.1%) with no accumulated deviation, and the two deliveries committed to date were met within the agreed deadline: Phase 1 on 07-09-2026 and Phase 2 part 1 on 30-09-2026. Activities not started and the reason. Three activities appear as not started, and in all three cases the reason is that their planned date has not yet arrived, not a failure to meet the plan. The implementation of the test environment and the functional tests are scheduled for (16-11 to 29-11). The user tests and the measurement of recognition accuracy are scheduled, once the facial module is closed. The migration to production, training sessions, manuals and the closure report are scheduled 8 and 9, with a deadline of 30-11-2026 according to the milestone schedule in the Project Charter. Activity in progress. The Facial Recognition module is in progress. It is implemented —capture, 128-dimension descriptor, comparison by Euclidean distance and configurable threshold— and the remaining work corresponds to tuning the threshold and the behavior under variable lighting, which by its nature requires successive empirical testing. Strategies to avoid affecting the project. The construction of the four microservices was brought forward relative to the Gantt Chart, so that the slack generated is devoted entirely to the final stretch of the schedule, which carries the highest risk because it concentrates testing, manuals and closure. Quality validation was distributed by module instead of being concentrated. And progress monitoring is maintained in the consolidated, which is updated at the close and makes it possible to detect a deviation in the two-week period in which it occurs and not at the end of the semester.

If the APT Project is a group project, in this column you must indicate the names of those responsible for each task or activity. This will later make it possible to differentiate the evaluation for each member.